Estimating: smarter guessing
Sebastian Bär
Image: “Sextant”, Blondinrikard Fröberg, CC BY 2.0

---
Why estimate?
- There is always someone who needs an ETA
- Estimating fosters work-breakdown and vice-versa
- Helps uncover tasks that you might otherwise forget
- Allows weighing gain against costs

---
Estimation Basics
Image: “Basic woodworking tools”, (c) Sebastian Bär

---
Estimation units
⊕	Easy to understand for
stakeholders
⊕	Easy to sum up
⊖	Harder to estimate
⊕	Easier to estimate
⊕	Easy to sum up
⊖	Should not be translated	to time
Stakeholders will do it anyway.
Person days or weeks
Complexity points

---
Expressing uncertainty: Fibonacci numbers
Fibonacci numbers express growing uncertainty
Estimated value
Actual

---
Expressing uncertainty: transparent buffers
Task	Estimation	Buffer	Buffer reason
Exchange unsupported external dependency	2	-	Interfaces identical, previous experiments shown good compatibility
Integration test + fix regressions	1	2
Performance test + fix regressions	1	8	First performance test with new library
Make release	< 1	-	Fully automatic
Roll out in customer’s environment	2	5	Customer did not confirm direct access yet. “Remote hands” a lot slower and more error prone
Total	7	15

---
Relative estimation: easier than absolute
Filter user list by creation date
8
Implementation
Unit test
UI test
User guide
Change log
Display login name uppercase
about as hard
Turn name into login name with underscores
2
2
Fix typo in UI
Reference is always 2
Implementation
Unit test
UI test
User guide
Change log
1
harder
trivial

---
Estimating together
Image: “Poker Chips”, slgckgc, CC-BY-SA 2.0

---
Planning poker
Add Spanish translation to the UI
13
1
2
3
5
8
21
34
55
89
∞

---
Planning poker – betting
Your estimation
(hidden)
1
2
3
21
34
55
89
∞
5
8

---
Planning poker
Everyone flips
their cards at the
same time.
1
2
3
21
34
55
89
∞
13
5
34
8
5
8

---
Planning poker – negotiation
We need the translation.
Our translation office offers Spanish too.
Spanish has lots of special characters.
We use UTF-8. No big deal.
1
2
3
5
8
21
34
55
89
∞
13
5
34
8

---
Planning poker – agreement (recommended)
Alright I can live with 8.
Player adapts
bet with new
information
1
2
3
5
8
21
34
55
89
∞
8
5
8
8

---
Planning poker – quorum (when in a hurry)
8 wins
13
1
2
3
5
21
34
55
89
∞
8
5
8
8

---
Planning poker – median (when in a hurry)
Median: 8 + 13 / 2 = 10.5
Estimation Result: 13
rounded to next higher Fibonacci number
Number of elements	odd	even
Median	Value that splits set in the middle	Sum of two middle values divided by two
Example	1, 3, 3, 5, 8, 13, 34 →5	1, 3, 3, 5, 8, 13, 13, 34 →5 + 8 / 2 = 6.5
13
5
34
8

---
Exercise
Use planning poker to estimate the following:
How many crew quarters does a 1.3 million barrel oil tanker have?
How many penguin species exist?
How many of those penguin species are on the red list?
How many months did it take to build the Eiffel tower?
[Speaker Notes: 1. Example for a BP oil tanker https://nassco.com/products/construction/commercial-construction/commercial-ship-portfolio/bp-tanker-fact-sheet/ crew size of up to 24. 2. 18 total, 11 on the red list according to https://www.birdlife.org/birds/list-of-penguin-species/ 3. 26 months according to https://houseunderconstruction.com/blog/how-long-did-it-take-build-eiffel-tower]

---
Estimation challenges
1. Large tasks and complex tasks
2. Vague specifications
3. First-of-a-kind tasks & known-unknows
4. Unknow-unknows

---
Challenge 1:
Large and complicated tasks
Image: “Mount McKinley”, Christoph Strässler, CC-BY-SA 2.0

---
Estimating an epic directly
Improve website accessibility
Epic
PO needs a quick estimation
The estimation will be very vague
Only useful as first indicator
Product Owner: 😱	Team: 😕
89

---
Task breakdown
Note that it doesn’t say “all tasks”. That is often unrealistic for complex epics.
Improve website accessibility
Compare scanners
Most tasks are considered
Understand challenges better
More transparency
Compare PO’s view with team’s
Will make progress more visible
Purchase license
Scan website
Fix findings
Product Owner: 😦	Team: 😐

---
Task estimation
Improve website accessibility
Compare scanners
Complex tasks visible
Shared understanding between PO and team
Purchase license
Scan website
Fix findings
Product Owner: 😐	Team: 😐
8
2
1
55

---
Sub-task breakdown
Improve website accessibility
Compare scanners
No more overly complex tasks
Better estimation
Reduced risk
Purchase license
Fix images
Scan website
Text-only variant
Fix findings
Add reader
Product Owner: 😐	Team: 🙂
8
2
1
Σ
5
13
13

---
Delimitation
Improve website accessibility
Add screen reader
Compare scanners
Valuable epic
Manageable size
Next epic cut out
Purchase license
Fix images
Scan website
Text-only variant
Fix findings
Add reader
Product Owner: 🙂	Team: 😀
8
2
1
Σ
5
13
13

---
Challenge 2:
Vague
specifications
Image: “Morning Fog on Golden Gate Bridge”, Grombo, CC-BY-SA 2.0

---
Backlog refinement session
Session 1
Session 2
Session 3
Team asks PO
to be more specific
PO calls users
Finds out page too slow
PO splits epic
One epic is easier to achieve
Team breaks down large one
PO picks up user complaint
writes it down
to not forget it
Team estimates high
PO specifies goals explicitly
Simpler solution available
Improve web page user experience
Improve page load times
Improve shop page load time
Average shop load time ≤ 0.1s
Improve report load time
Average report load time ≤ 3s
Replace database
 Increase RAM size
…
89
55
8
34
8
2
21
2

---
Exercise
Determine how long it takes from firing the 1 o’clock gun on Edinburgh Castle until ships in the harbor hear the signal
Break epic down into tasks
Improve epic specification
Estimate tasks
Stop time while you solve the puzzle
Compare with estimates

---
Challenge 3:
First-of-a-kind tasks
&
known-unknows
Image: “AS11-44-6642”, courtesy of the Earth Science and
Remote Sensing Unit, NASA Johnson Space Center

---
Spikes
Session 1
Spikes
Session 2
Team asks PO
to plan spikes
Team estimates required timebox
PO & team agree on timebox
Team experiments with unknown task
Experiments ranked by risk (descending)
PO brings an epic with at least one totally unknown task
Team applies learning successes to breakdown and estimation
✅
EV battery predictive maintenance
Spike: Import battery data
Spike: Import battery data
Spike: Import battery data
[2]
[2]
[2]
✅
Network setup
Spike: Compare ML algorithms
Spike: Compare ML algorithms
[5]
[5]
Mass data import
EV battery predictive maintenance
EV battery predictive maintenance
…
89
Risk
55

---
Exercise
Estimate epic directly (person seconds)
Break epic down into tasks
Plan a spike to find fast strategy
Time-box the spike
Run the spike (mind the time box!)
Re-estimate tasks
Stop time while you solve the puzzle
Compare with estimates
Roll 100 D6.
Record rolls.
Sum up.
[Speaker Notes: Team needs to realize that estimating with poker cards requires multiplier During break down the team will need to discuss that “record rolls” is an ambiguous requirement. They need to agree on what “record rolls” means and write it down. In the spike they can try multiple strategies. But that is not required. If they agree on what the criteria for “fast” is, one can be enough. Keeping the time box is important. The trainer should give feedback on time box adherence Remind the trainees that this should also scale to larger numbers.]

---
Challenge 4:
Unknown-unknows
Image: “UFO sighting in Louisiana”, DragonRal, CC-BY-SA 2.0

---
Dealing with unknown-unknows
If you were hoping for a silver bullet, prepare to be disappointed.
Unknown-unknowns are an inherent risk of any complex task.
Repetition helps reducing them.
Otherwise all involved parties need to understand that estimations can an will be off. Sometimes more, at other times less.

---
Summary
1. Make the goals concrete and precise
2. Break down large tasks
3. Estimate tasks and sum up
4. Break down further where possible
5. Use planning poker
6. Be aware that estimates can be wrong

---
Successful estimation everyone!
Image:
“Estimation Poker Straight Flush”,
Joel Bez, CC-BY